## Daily Report
DAILY REPORT - 01-05-2026
Project / Module | assignTo | Task Description | Phase | Start Date | End Date | Est. (HH:MM:SS) | Logged (HH:MM:SS) | Priority | Status
CRM ¦ Core | Abhishek Kumar Sharma | orking on registration, login, OTP, and reseller form validation bugs — fixing input limits, error messages, and Google OAuth redirect issues. | - | 04-05-2026 | 04-05-2026 | 06:30:00 | 00:00:00 | MEDIUM | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on landing page and bugs resolving | - | 06-05-2026 | 06-05-2026 | 08:00:00 | 06:07:39 | MEDIUM | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | working on landing page | - | 07-05-2026 | 07-05-2026 | 08:00:00 | 05:04:37 | MEDIUM | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | working on landing page | - | 08-05-2026 | 08-05-2026 | 07:00:00 | 05:05:06 | MEDIUM | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | working on landing page | - | 11-05-2026 | 11-05-2026 | 06:30:00 | 00:00:00 | MEDIUM | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on landing page | - | 12-05-2026 | 12-05-2026 | 08:00:00 | 05:17:07 | MEDIUM | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | working on profile setup form validations and landing page redesign | - | 13-05-2026 | 13-05-2026 | 08:00:00 | 00:00:00 | MEDIUM | DELAYED
CRM ¦ Core | Abhishek Kumar Sharma | Currently integrating AWS SES and Razorpay payment gateway | - | 14-05-2026 | 14-05-2026 | 08:00:00 | 06:50:16 | HIGH | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on Razorpay payment gateway integration | - | 15-05-2026 | 15-05-2026 | 08:00:00 | 05:28:22 | HIGH | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on fixing UI bugs | - | 18-05-2026 | 18-05-2026 | 08:00:00 | 07:26:32 | MEDIUM | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on Customer module bugs | - | 19-05-2026 | 19-05-2026 | 07:00:00 | 05:39:16 | MEDIUM | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on Lead Management & Contacts module | - | 20-05-2026 | 20-05-2026 | 07:00:00 | 00:00:00 | MEDIUM | DELAYED
CRM ¦ Core | Arun Kashyap | meeting with Arun | - | 20-05-2026 | 20-05-2026 | 01:30:00 | 00:00:00 | MEDIUM | DELAYED
CRM ¦ Core | Abhishek Kumar Sharma | Working on: Inventory Management System | - | 21-05-2026 | 21-05-2026 | 08:00:00 | 07:42:05 | HIGH | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on: Inventory Management | - | 22-05-2026 | 22-05-2026 | 07:00:00 | 06:28:49 | HIGH | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on building 3 separate inventory pages | - | 25-05-2026 | 25-05-2026 | 08:00:00 | 00:00:00 | HIGH | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on building 3 separate inventory pages | - | 26-05-2026 | 26-05-2026 | 07:00:00 | 05:39:13 | HIGH | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | working on multiple bugs | - | 27-05-2026 | 27-05-2026 | 08:00:00 | 05:10:19 | MEDIUM | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on LoginName-based authentication system | - | 28-05-2026 | 28-05-2026 | 08:00:00 | 07:00:39 | HIGH | COMPLETED
CRM ¦ Core | Abhishek Kumar Sharma | Working on loginName authentication system and resolving bugs | - | 29-05-2026 | 29-05-2026 | 08:00:00 | 06:08:34 | MEDIUM | COMPLETED
Performance Summary
Total Tasks Assigned | 20
Tasks Completed | 17
Tasks In Progress | 0
Tasks Open | 0
Total Estimated Hours | 145.5
Total Logged Hours | 85.1
Completion Rate | 85%
Average Efficiency | 0.59